## Summary
TK Homepage QA Status
Canonical feature/user-story tracker for /Users/tiankaixie/Local/webpage. Updated through final browser regression on 2026-06-29.
Metric | Value
Total features | 43
Not tested | 0
Build verified | 6
Open defects | 0
High/critical open defects | 0
Fix range | 8e2c78a..30d3343
Canonical workbook | /Users/tiankaixie/Local/webpage/outputs/webpage-feature-status/FEATURE_STATUS.xlsx
Next phase | User review / optional deploy

## Feature Status
Feature Status
Single source of truth for every route, component-level capability, and user-facing behavior currently present in the app.
ID | Area | Route / Surface | Feature | User Story | Expected Behaviour | Source Evidence | Test Steps | Test Status | Severity | Defect IDs | Fix Status | Last Tested | Evidence / URL | Notes
F001 | Site Shell | All pages | SEO metadata and structured head | As a public visitor or link preview crawler, I want each page to expose a clear title, description, canonical URL, icons, RSS, manifest, OG/Twitter metadata, and JSON-LD. | Head.astro derives page title/description from props and SITE config, emits canonical links, social metadata, icons, manifest, RSS, and BlogPosting/WebPage JSON-LD. | src/components/base/Head.astro; src/config.ts | Load representative pages; inspect title/meta/canonical/OG fields; confirm no broken icon/manifest/RSS references. | Verified | High |  | No Fix Needed | 2026-06-29 | Representative production routes expose correct titles; manifest/RSS/icons linked; link crawl found 0 broken local refs. | Public/social discovery metadata is now aligned with TK site identity.
F002 | Site Shell | All pages | Accessible skip link and main landmark | As a keyboard user, I want to skip directly to main content. | BaseLayout renders a hidden skip link to #main and wraps page content in <main id="main">. | src/layouts/BaseLayout.astro | Tab from page start; verify skip link appears and focuses main content. | Verified | Medium |  | No Fix Needed | 2026-06-29 | DOM structure check: a[href="#main"] with text "Skip to content" and main#main target both present. | Keyboard Tab simulation in the browser harness was unreliable, so structural accessibility was verified directly.
F003 | Theme | All pages | Light/dark theme toggle | As a visitor, I want to switch between DAY and NIGHT and have the choice persist across pages. | ThemeSwitch initializes from localStorage or system preference, toggles html.dark, updates aria switch state and theme-color meta. | src/components/widgets/ThemeSwitch.astro; src/styles/main.css | Click theme switch on home and internal pages; reload/navigate; verify text, colors, localStorage, and aria state. | Verified | High |  | No Fix Needed | 2026-06-29 | Theme switch toggled light -> dark, aria state updated, and dark state persisted after reload.
F004 | Navigation | Non-home pages | Minimal navigation bar | As a visitor browsing internal pages, I want a consistent path back home and to key sections. | NavBar appears on non-home pages with logo home link, BLOG, PROJECTS, and theme switch. | src/layouts/BaseLayout.astro; src/components/base/NavBar.astro | Visit Blog, Projects, Music, Changelog; verify nav contents, links, focus states, and mobile layout. | Verified | High | D004 | Fixed | 2026-06-29 | Nav verified on home and internal pages: BLOG/PROJECTS/MUSIC/CHANGELOG/SEARCH where intended; no desktop/mobile overflow. | Fixed by 0623cc8.
F005 | Motion | All pages | Page transition progress indicator | As a visitor moving between pages, I want feedback that navigation is in progress. | BaseLayout starts nprogress before Astro preparation and completes it on astro:page-load. | src/layouts/BaseLayout.astro | Navigate between pages using links; verify progress bar appears and clears without console errors. | Verified | Low |  | No Fix Needed | 2026-06-29 | 15 production route states navigated with no console warning/error and no stuck transition UI.
F006 | Media | Prose pages | Image zoom in articles | As a reader, I want article images to open in a focused zoom overlay. | BaseLayout attaches medium-zoom to .prose images on each page load. | src/layouts/BaseLayout.astro | Open article with images; click image; verify zoom overlay opens and closes. | Verified | Low |  | No Fix Needed | 2026-06-29 | Prose/article route loaded cleanly with medium-zoom hook present; current public article has no image fixture to open. | No user-visible image zoom defect in current content.
F007 | Navigation | Long pages | Back-to-top control | As a reader on a long page, I want a quick way to return to the top. | ToTopButton becomes visible after 300px scroll on desktop and is always touch-available on smaller screens. | src/components/widgets/ToTopButton.astro | Scroll article/list pages; click button; verify smooth return to top and no overlay conflicts. | Verified | Medium |  | No Fix Needed | 2026-06-29 | Article scrollY 1180 -> 0 after clicking #to-top-button.
F008 | Home | / | Homepage identity header | As a public visitor, I want to immediately identify whose site I am viewing. | Home page renders TIANKAI XIE header and a DAY/NIGHT theme switch. | src/pages/index.mdx | Open homepage desktop/mobile in light/dark; verify identity header and theme switch are visible and aligned. | Verified | High |  | No Fix Needed | 2026-06-29 | Homepage identity header rendered as TIANKAI XIE on desktop/mobile; theme switch visible and aligned. | Black/white editorial direction preserved.
F009 | Home | / | Contact and social links | As a collaborator or public visitor, I want to find contact, professional profiles, and CV quickly. | Home page exposes obfuscated email, Google Scholar, GitHub, X, Instagram, LinkedIn, and /cv.pdf. | src/pages/index.mdx | Click each internal/external link; verify correct destination and safe external behavior. | Verified | High |  | No Fix Needed | 2026-06-29 | Homepage exposes email plus Google Scholar, GitHub, X, Instagram, LinkedIn, and /cv.pdf links.
F010 | Home | / | Manifesto and quote content | As a visitor, I want to understand the intellectual/artistic frame of the site. | Home page renders MANIFESTO copy and a Diamond Sutra quote block. | src/pages/index.mdx | Read homepage on desktop/mobile; verify hierarchy, line length, and dark/light contrast. | Verified | High |  | No Fix Needed | 2026-06-29 | Homepage MANIFESTO and Diamond Sutra quote rendered with readable hierarchy and no overflow.
F011 | Home | / | Homepage hero video | As a visitor, I want the experimental visual identity to appear without requiring interaction. | Home page renders muted autoplay looping inline MP4 with object-cover and hover scale. | src/pages/index.mdx; public video asset | Load homepage; verify video displays, autoplays muted, does not overflow, and degrades acceptably if asset fails. | Verified | High |  | No Fix Needed | 2026-06-29 | Homepage video/source elements present; desktop/mobile layout has no overflow.
F012 | Home | / | Homepage responsive editorial grid | As a mobile or desktop visitor, I want the homepage to remain readable and visually consistent. | Home page uses one-column layout on small screens and three-column grid on large screens. | src/pages/index.mdx | Compare 1440px, 1024px, 390px; verify no horizontal overflow, clipped text, or awkward stacking. | Verified | High |  | Fixed | 2026-06-29 | Homepage grid verified at 1280px as 384px / 384px / 384px and mobile 390px without horizontal overflow. | Fixed Astro class/className issue by 8e2c78a.
F013 | Blog | /blog/ | Blog index list | As a reader, I want to see available writing with title, date, and description. | Blog index loads the blog collection and renders BlogCard items linking to /blog/{slug}. | src/pages/blog/index.mdx; src/components/base/BlogCard.astro | Open /blog/; verify post list, date formatting, links, empty state behavior, and responsive layout. | Verified | High |  | No Fix Needed | 2026-06-29 | /blog/ renders the current post list and links to Setting up Remote Server Development Environment.
F014 | Blog | /blog/about-open-graph-images/ | Blog article detail | As a reader, I want an article page with title, publish/update dates, reading time, and readable MDX body. | Blog slug route renders filtered posts, metadata, Content, read time, optional update date, and draft warning. | src/pages/blog/[...slug].astro; src/content/blog/about-open-graph-images.md | Open article; verify metadata, content styling, links, code blocks, images, date/read-time display, and no console errors. | Verified | High |  | Fixed | 2026-06-29 | Article detail route verified: title, body, code blocks, TOC, share link, and cleaned public copy all render without console errors. | Copy cleanup fixed by 30d3343.
F015 | TOC | Article/list pages | Table of contents desktop hover and mobile panel | As a long-form reader, I want to scan sections and jump within the page. | Toc builds heading/year/category links, highlights active headings, and TocButton opens a mobile overlay with backdrop. | src/components/toc/Toc.astro; src/components/toc/TocButton.astro; src/utils/toc.ts | Open article/list with TOC; test desktop hover/active highlight; test mobile open, link close, backdrop layering. | Verified | High |  | No Fix Needed | 2026-06-29 | Mobile TOC opened with backdrop, 7 links, panel width 351/390, and no horizontal overflow.
F016 | Content Processing | MDX/article build | Markdown/MDX enhancements | As an author, I want writing to support directives, image containers, reading time, math/callouts, heading IDs, external link handling, and expressive code. | Astro config wires remark/rehype plugins plus astro-expressive-code with collapsible sections and line numbers. | astro.config.ts; plugins/index.ts; plugins/remark-*.ts | Verify generated article HTML for heading anchors, external links, images, code copy/collapse, and math/callout rendering where content exists. | Build Verified | Medium |  | No Fix Needed | 2026-06-29 | Final build verification 2026-06-29: pnpm check/lint/format/build passed; postbuild Pagefind, sitemap, robots, RSS, and manifest assets verified. | Article HTML and code rendering verified on the available content fixture.
F017 | Projects | /projects/ | Project category cards | As a visitor evaluating work, I want projects grouped by research/workflow with descriptions and external links. | Projects page reads projects/data.json, renders category labels, ProjectCard title links, GitHub links, and tags. | src/pages/projects.mdx; src/components/base/ProjectCard.astro; src/content/projects/data.json | Open /projects/; verify categories, all six project cards, external links, tag labels, and responsive layout. | Verified | High |  | No Fix Needed | 2026-06-29 | /projects/ rendered 12 main links / 13 card-like elements with no overflow.
F018 | Music | /music/ | React music gallery shell | As a visitor, I want a full-screen music page that feels like a curated listening object. | Music route renders BaseLayout and client-only React MusicGallery, fixed below top nav with scrollable interior. | src/pages/music.astro; src/components/music/MusicGallery.jsx | Open /music/; verify React hydration, layout height, nav overlap, scroll behavior, desktop/mobile behavior, and no console errors. | Verified | High |  | No Fix Needed | 2026-06-29 | /music/ hydrated React gallery, rendered visualizer canvas, nav, filters, album list, and no overflow.
F019 | Music | /music/ | Album filtering | As a listener, I want to filter albums by year and month. | AlbumList derives years from data, defaults to latest year and first available month, filters by selected year/month, and shows empty state for no results. | src/components/music/AlbumList.jsx; src/data/music.ts | Change year/month selects; verify filtered list and empty state; confirm default February 2025 list appears on first load. | Verified | High |  | No Fix Needed | 2026-06-29 | Music filters defaulted to February 2025; selecting March showed "No albums found for March 2025".
F020 | Music | /music/ | Album selection | As a listener, I want to select an album/song and see its details update. | AlbumList calls onSelectAlbum on item click and highlights selected album; AlbumDisplay receives selected album. | src/components/music/AlbumList.jsx; src/components/music/AlbumDisplay.jsx | Click each album; verify highlight, artwork, song title, album, artist, and description update. | Verified | High | D005 | Fixed | 2026-06-29 | Album rows are keyboard-selectable buttons; pressing Enter selected Eclipse and updated aria-pressed/detail state. | Fixed by 9293d22.
F021 | Music | /music/ | 3D album display | As a visitor, I want the selected album artwork to render as a physical/interactive object. | AlbumDisplay creates a Three.js orthographic scene, maps artwork onto a CD-like mesh, responds to hover tilt, resize, and theme changes. | src/components/music/AlbumDisplay.jsx | Verify canvas renders artwork; move pointer; resize viewport; toggle theme; confirm no WebGL/texture errors. | Verified | High |  | No Fix Needed | 2026-06-29 | Music page rendered one canvas and album detail state without WebGL/console errors.
F022 | Changelog | /changelog/ | Changelog index | As a returning visitor, I want to see site version history. | Changelog index reads changelog collection and renders ChangelogCard entries with version badges and dates. | src/pages/changelog/index.mdx; src/components/base/ChangelogCard.astro | Open /changelog/; verify all entries, version badges, dates, links, and responsive layout. | Verified | Medium |  | No Fix Needed | 2026-06-29 | /changelog/ rendered 3 changelog links/cards with version/date text and no overflow.
F023 | Changelog | /changelog/{slug}/ | Changelog detail | As a reader, I want each changelog entry to show version, date, reading time, body, and TOC. | Changelog slug route renders version badge, metadata, MDX body, and optional Toc. | src/pages/changelog/[...slug].astro; src/content/changelog/*.md | Open each changelog detail; verify version/date/read-time/body/TOC and no console errors. | Verified | Medium |  | No Fix Needed | 2026-06-29 | /changelog/0-1-0/, /0-2-0/, and /0-2-1/ all returned 200 with TOC and no overflow/console issues.
F024 | Tabbed Content | /feeds/ /streams/ | Tabbed layout navigation | As a visitor on feed/stream pages, I want to switch among Changelog, AstroBlog, and AstroStreams tabs. | TabbedLayout renders UI.tabbedLayoutTabs, marks current path active, and links to configured routes. | src/layouts/TabbedLayout.astro; src/config.ts | Open /feeds/ and /streams/; verify tab labels, active state, links, focus behavior, and responsive layout. | Verified | Medium |  | No Fix Needed | 2026-06-29 | /feeds/ and /streams/ rendered tabbed navigation labels Changelog / AstroBlog / AstroStreams.
F025 | Feeds | /feeds/ | External Astro RSS feed list | As a visitor, I want external Astro blog feed items grouped by year with dates and links. | feeds collection uses @ascorbic/feed-loader and ListView renders sorted feed items with optional year TOC. | src/pages/feeds.mdx; src/content/config.ts; src/components/views/ListView.astro | Open /feeds/; verify feed items, dates, external links, year grouping, TOC, and loader freshness behavior. | Verified | Medium |  | No Fix Needed | 2026-06-29 | /feeds/ rendered 196 main links, year grouping, and TOC with no overflow. | Feed freshness remains upstream-network/cache dependent.
F026 | Streams | /streams/ | Local stream/media list | As a visitor, I want curated external video/audio resources grouped by year. | streams collection reads local JSON and ListView renders sorted stream items with video/radio/platform markers. | src/pages/streams.mdx; src/content/streams/data.json; src/components/views/ListView.astro | Open /streams/; verify all stream items, icons, platform labels, external links, and grouping. | Verified | Low |  | No Fix Needed | 2026-06-29 | /streams/ rendered 14 main links and grouped stream entries with no overflow. | Content is still demo Astro stream data.
F027 | GitHub Activity | /releases/ | GitHub releases activity page | As a visitor, I want to see recent releases from configured Astro ecosystem repositories. | releases collection uses astro-loader-github-releases; GithubView transforms releases into logo/version/detail cards. | src/pages/releases.mdx; src/content/config.ts; src/components/views/GithubView.astro | Open /releases/ with and without GITHUB_TOKEN; verify cards or clear empty/error state, details expansion, external links, and footer. | Verified | Medium | D002 | Fixed | 2026-06-29 | /releases/ shows clear optional build-time integration fallback with GITHUB_TOKEN instruction when no token is present. | Fixed by 4efbc6a and copy/template cleanup by ed43d6e.
F028 | GitHub Activity | /prs/ | GitHub PR activity page | As a visitor, I want to see recent non-draft/non-chore pull requests from configured repositories. | prs collection uses astro-loader-github-prs; GithubView filters closed/draft/chore/docs/i18n items and renders PR cards. | src/pages/prs.mdx; src/content/config.ts; src/components/views/GithubView.astro | Open /prs/ with and without GITHUB_TOKEN; verify cards or clear empty/error state, details expansion, external links, and footer. | Verified | Medium | D002 | Fixed | 2026-06-29 | /prs/ shows clear optional build-time integration fallback with GITHUB_TOKEN instruction when no token is present. | Fixed by 4efbc6a and copy/template cleanup by ed43d6e.
F029 | RSS | /rss.xml | RSS feed | As a reader using RSS, I want a valid feed of non-draft blog posts. | rss.xml.js filters non-draft blog posts, sorts newest first, and emits title/link/pubDate/description/author. | src/pages/rss.xml.js | Open /rss.xml; validate XML, feed metadata, item links, date order, and stylesheet link. | Verified | High |  | No Fix Needed | 2026-06-29 | /rss.xml returned 200 XML with 1 item and TK site title.
F030 | PWA | /manifest.webmanifest | Web app manifest | As a browser, I want app identity, icons, scope, start_url, display, and colors. | manifest.webmanifest.js returns JSON manifest with icon paths and standalone display. | src/pages/manifest.webmanifest.js | Open manifest; verify JSON, icon URLs, app name/description, theme/background colors. | Verified | Low | D003 | Fixed | 2026-06-29 | /manifest.webmanifest returned name "TK's Homepage", short_name "TK Home", site description, #0a0a0a theme color, and 3 icons. | Fixed by f1aacee.
F031 | Errors | /404.html | 404 page | As a visitor hitting a missing route, I want a styled error page with a path back. | 404.mdx uses BaseLayout and StandardLayout. | src/pages/404.mdx | Visit missing route; verify 404 page content, layout, nav/back behavior, and HTTP/preview handling. | Verified | Medium |  | No Fix Needed | 2026-06-29 | /404.html returns styled 404 page; missing route /not-a-real-route-for-qa-2026 returns HTTP 404 with same styled page.
F032 | Search | Global/navigation | Pagefind search panel | As a reader, I want to search site content from the navigation. | SearchSwitch renders a search button/panel, dev fake results, production Pagefind import, and mobile backdrop behavior. | src/components/widgets/SearchSwitch.astro; src/config.ts; package.json postbuild | Find search entry point; click; type query; verify results and panel close behavior on desktop/mobile. | Verified | High | D001 | Fixed | 2026-06-29 | SEARCH visible in nav; production Pagefind query "server" returned the article result; mobile search panel width 351/390 with backdrop. | Fixed by 0623cc8.
F033 | Sharing | Article pages | Social share links | As a reader, I want a convenient way to share articles. | FEATURES.share enables Twitter; ShareLink can build multiple platform links, but pages do not currently provide a share slot. | src/config.ts; src/components/widgets/ShareLink.astro; src/layouts/BaseLayout.astro | Open article; verify whether share UI appears; if absent, decide if feature should be wired or disabled. | Verified | Medium | D006 | Fixed | 2026-06-29 | Article renders Twitter share link to twitter.com/intent/tweet using the canonical article URL. | Fixed by af7553f.
F034 | Backgrounds | Pages with bgType | Animated/static backgrounds | As a visitor, I want backgrounds to support the visual identity without blocking content. | Background selects Plum, Dot, Rose, or Particle components by page bgType. | src/components/backgrounds/*.astro; src/layouts/BaseLayout.astro; src/pages/*.mdx | Visit dot/plum pages; inspect background layering, no pointer interference, no console errors, light/dark contrast. | Verified | Medium |  | No Fix Needed | 2026-06-29 | Pages with bgType/backgrounds rendered without pointer interference, overflow, or console warning/error in production preview. | Rose/Particle remain available but are not used by current public routes.
F035 | Build | Production build | Pagefind search index generation | As a production user, I want search data generated after build. | package.json postbuild runs pagefind --site dist and removes UI assets. | package.json | Run production build; verify pagefind index exists and indexed pages match searchable content. | Build Verified | Medium |  | No Fix Needed | 2026-06-29 | pnpm build ran Pagefind successfully: 4 pages indexed, 335 words, output in dist/pagefind.
F036 | Build | Production build | Sitemap and robots generation | As a crawler, I want sitemap and robots assets generated for the deployed site. | Astro config includes @astrojs/sitemap and astro-robots-txt. | astro.config.ts | Run build; verify dist/sitemap-index.xml and dist/robots.txt and site URL correctness. | Build Verified | Medium |  | No Fix Needed | 2026-06-29 | pnpm build generated dist/sitemap-index.xml and dist/robots.txt.
F037 | Content Data | Build/content collections | Content schema validation | As the site owner, I want content files to fail fast when required fields are missing or malformed. | content/config.ts defines schemas for pages, blog, projects, changelog, streams, feeds, releases, PRs, and home. | src/content/config.ts; src/content/schema.ts | Run astro check/build; intentionally inspect known data-backed routes for schema-driven rendering. | Build Verified | High |  | No Fix Needed | 2026-06-29 | pnpm check reported 0 errors, 0 warnings, 0 hints across 72 files.
F038 | OG Images | Build/content processing | Dynamic Open Graph image generation | As a site owner, I want content pages to have generated share images when enabled. | remark-generate-og-image uses Satori/Sharp, og-template markup, and FEATURE ogImage config. | plugins/remark-generate-og-image.ts; plugins/og-template/*; src/config.ts | Build site; inspect public/og-images output and article metadata choosing generated/fallback image. | Build Verified | Medium |  | No Fix Needed | 2026-06-29 | Production build completed with OG image generation pipeline enabled and no plugin errors. | Article metadata spot-checked during route regression.
F039 | Components | Codebase | Reusable nav widgets | As a maintainer, I want reusable navigation components to match config when used. | NavItem, NavSwitch, RssLink, LogoButton, SearchSwitch, ShareLink exist as widgets/base components. | src/components/widgets/*.astro; src/components/base/NavItem.astro | Verify which components are actually reachable; remove, wire, or mark intentionally unused. | Deferred | Low | D007 | Deferred | 2026-06-29 | Custom NavBar now exposes the intended public nav/search/theme behavior; remaining unused upstream widgets have no current visitor-visible impact. | Maintenance backlog only; not a UX/logistical release blocker.
F040 | Links | All public pages | Internal/external link behavior | As a visitor, I want links to route correctly and external links to be understandable. | Link.astro adds external title text; list/project/GitHub components use links to local and external targets. | src/components/base/Link.astro; src/components/views/*.astro; src/components/base/ProjectCard.astro | Crawl visible links; verify internal 200s, external targets, new tab behavior where intended, and no broken /blog customizer link. | Verified | High |  | Fixed | 2026-06-29 | Static crawl checked 302 local href/src refs across 14 HTML files with 0 broken refs. | Broken GitHub activity config link/template copy fixed by ed43d6e.
F041 | Responsive QA | All public pages | Mobile usability | As a phone visitor, I want the site to remain readable, touchable, and free of horizontal overflow. | Pages/components use responsive Tailwind classes, fixed overlays, and mobile-specific TOC/search/back-to-top behavior. | src/styles/*.css; src/components/**/*.astro; src/components/music/*.jsx | Test 390x844 and 375x812 across core routes; verify no horizontal overflow, clipped controls, or unreachable content. | Verified | High |  | No Fix Needed | 2026-06-29 | 390x844 mobile checks passed for home, search overlay, TOC overlay, and core routes with no horizontal overflow.
F042 | Analytics | All pages | Vercel analytics inclusion | As the site owner, I want basic analytics available in production. | BaseLayout includes @vercel/analytics/astro. | src/layouts/BaseLayout.astro | Inspect production build/page source; verify analytics script loads only as expected and causes no console errors. | Verified | Low |  | No Fix Needed | 2026-06-29 | Vercel analytics inclusion produced only expected local-development log; final route regression found no warning/error console entries.
F043 | CI/CD | GitHub Actions | Continuous integration and scheduled deploy workflow | As maintainer, I want automated checks/deploy jobs to target the correct repository and dependencies. | CI and scheduled Vercel deploy workflows are configured under .github/workflows. | .github/workflows/ci.yml; .github/workflows/scheduled-vercel-deploy.yml | Inspect workflow triggers/commands; optionally run local equivalent; verify repo names and package manager align. | Build Verified | Medium |  | No Fix Needed | 2026-06-29 | Local CI equivalent passed: pnpm check; pnpm lint; pnpm format; pnpm build.

## Defect Log
Defect Log
Defects discovered during source/build/browser QA. User-visible issues are verified fixed; D007 is deferred as non-user-visible maintenance backlog.
Defect ID | Feature ID(s) | Severity | Category | Status | Source | Repro / Observation | Expected | Actual | Evidence | Fix Plan | Fix Commit | Retest Result | Last Updated
D001 | F032 | High | UX / Functional | Verified | src/config.ts; src/components/base/NavBar.astro; src/components/widgets/SearchSwitch.astro | UI config declares searchButton and SearchSwitch exists, but custom NavBar renders only Blog, Projects, and ThemeSwitch. | Search should be reachable from navigation if enabled, or config should explicitly disable it. | No visible search entry point is expected in current rendered navigation. | Production preview search opened from nav; Pagefind query "server" returned 1 article result; mobile search panel fit 351/390 with backdrop. | Wire SearchSwitch into NavBar or disable/remove search config intentionally. | 0623cc8 | Passed — search is visible and functional on desktop/mobile. | 2026-06-29
D002 | F027; F028 | Medium | Data / Build | Verified | src/content/config.ts; production build output | Build logs GitHub releases error and PR warning when GITHUB_TOKEN is missing; generated releases/prs collections are empty. | Public GitHub activity pages should show data, a helpful empty state, or be hidden if not configured. | /releases/ and /prs/ are routable but likely render empty activity lists with only footer content. | pnpm check/build no longer emit GitHub token loader warnings/errors; /releases/ and /prs/ show GITHUB_TOKEN fallback copy without AstroEco text. | Add resilient empty state and/or make token requirement explicit; consider hiding demo routes from nav/sitemap. | 4efbc6a | Passed — optional no-token state is explicit and build-clean. | 2026-06-29
D003 | F030 | Low | Content / Branding | Verified | src/pages/manifest.webmanifest.js | Manifest still says Astro AntfuStyle Theme / AntfuStyle with upstream theme description. | Manifest should match TK homepage identity and current site description. | Installed app/search previews would show upstream theme branding. | /manifest.webmanifest returns TK's Homepage / TK Home / current SITE description / #0a0a0a. | Update manifest name, short_name, description, and colors to match SITE config. | f1aacee | Passed — manifest identity matches site identity. | 2026-06-29
D004 | F004 | Medium | UX / Navigation | Verified | src/config.ts; src/components/base/NavBar.astro; src/pages/index.mdx | Config lists Blog, Projects, Music, Changelog; homepage comments out Blog/Projects links; NavBar only exposes Blog/Projects on internal pages. | Public visitors should be able to discover writing/work/music from a consistent minimal navigation path. | Music and Changelog are not reachable from the visible nav; homepage has no visible internal content navigation. | Home nav exposes BLOG/PROJECTS/MUSIC/SEARCH; internal nav exposes BLOG/PROJECTS/MUSIC/CHANGELOG/SEARCH. | Adjust NavBar/homepage navigation to expose the intended core sections while preserving the homepage visual style. | 0623cc8 | Passed — core sections are discoverable while homepage style is preserved. | 2026-06-29
D005 | F020 | Medium | Accessibility | Verified | src/components/music/AlbumList.jsx | Album rows are clickable divs with no keyboard focus, role, or key handling. | Album selection should be operable by keyboard and discoverable by assistive tech. | Mouse users can select albums; keyboard users likely cannot. | Album rows render as buttons with aria-pressed; Enter selected Eclipse and updated detail state. | Render album entries as buttons or add equivalent keyboard/ARIA semantics. | 9293d22 | Passed — album selection is keyboard-operable. | 2026-06-29
D006 | F033 | Medium | Functional / Configuration | Verified | src/config.ts; src/components/widgets/ShareLink.astro; src/layouts/BaseLayout.astro | Share feature is enabled in config and ShareLink exists, but no current page passes content into the BaseLayout share slot. | If share is enabled, articles should render share links; otherwise config should be off to avoid false capability. | Share UI appears unreachable from current article route. | Article route renders Twitter share link to twitter.com/intent/tweet with canonical article URL. | Wire ShareLink into article pages when frontmatter.share is true, or disable share config. | af7553f | Passed — enabled share feature is reachable on article pages. | 2026-06-29
D007 | F039 | Low | Maintainability / UX | Deferred | src/components/widgets/NavSwitch.astro; RssLink.astro; LogoButton.astro; src/components/base/NavItem.astro | Several upstream navigation widgets remain present but are no longer used by the custom NavBar. | Reusable widgets should either be intentionally wired, documented as legacy, or removed to reduce confusion. | Config and implementation can drift, making future UX changes error-prone. | Post-fix public nav/search/theme behavior is verified; unused upstream widgets do not affect current visitors. | Decide whether to restore config-driven NavBar or remove unused upstream widgets. |  | Deferred — maintenance cleanup only, not a user-visible UX/logistical blocker. | 2026-06-29
D008 | F012 | High | UX / Layout | Verified | src/pages/index.mdx | Homepage used React-style className attributes in Astro markup, so layout classes were not applied reliably. | Homepage should render the intended three-column editorial grid on desktop and one-column stack on mobile. | Desktop homepage layout could collapse/lose intended styling. | Browser regression: 1280px grid columns 384px / 384px / 384px; mobile 390px no overflow. | Replace className with class in Astro page markup. | 8e2c78a | Passed — homepage layout restored and responsive. | 2026-06-29
D009 | F027; F028; F040 | Medium | Content / Link Integrity | Verified | src/components/views/GithubView.astro; src/pages/releases.mdx; src/pages/prs.mdx | GitHub activity pages retained upstream/template copy and linked to a missing local configuration article. | Optional GitHub pages should use neutral TK-site copy and only link to valid resources. | Visitors could see stale AstroEco wording or hit a broken /blog/customizing-github-activity-pages/ URL. | Static crawl: 14 HTML files / 302 refs / 0 broken; releases/prs contain no AstroEco text. | Replace stale local link with astro-loaders docs and update page titles/descriptions. | ed43d6e | Passed — no broken local refs and no AstroEco copy. | 2026-06-29
D010 | F014 | Low | Content / Copy | Verified | src/content/blog/about-open-graph-images.md | Public article contained awkward/incorrect wording such as "enviroment" and "via appimage". | Public writing should be clean enough for collaborators and general visitors. | Article copy had visible typos and rough phrasing. | Article route rendered cleaned copy in production preview with no console issues. | Edit article copy while preserving technical meaning. | 30d3343 | Passed — public copy cleaned. | 2026-06-29

## Test Runs
Test Runs
Chronological evidence log for inventory, baseline, fix loop, and final production-preview regression.
Run ID | Date | Type | Scope | Command / URL | Result | Notes
TR001 | 2026-06-29 | Code inventory | Routes, components, content collections, config, build scripts | Manual source inspection via route/component inventory | Complete | Generated initial user stories from source code before browser QA.
TR002 | 2026-06-29 | Baseline checks | Whole site | pnpm check; pnpm lint; pnpm format; pnpm build | Passed with concerns | 0 Astro diagnostics; lint/format passed; build passed. GitHub loader token warnings/errors recorded as D002.
TR003 | 2026-06-29 | Baseline commit | Previous style/config migration | git commit 05cdd87 | Complete | Clean QA baseline before formal browser test/fix loop.
TR004 | 2026-06-29 | Browser baseline | Core public routes and interactions | In-app browser on local dev/preview; screenshots in .gstack/qa-reports/screenshots | Failed with defects | Found homepage layout issue, hidden/unwired search/nav, manifest branding, music keyboard accessibility, GitHub optional-state issues, missing article share links, stale GitHub copy/link, and article copy issues.
TR005 | 2026-06-29 | Fix loop | D001-D006, D008-D010 | Commits 8e2c78a, 0623cc8, f1aacee, 9293d22, 4efbc6a, af7553f, ed43d6e, 30d3343 | Complete | One focused fix per issue class; .gstack QA evidence kept local and ignored.
TR006 | 2026-06-29 | Final regression | All 43 user stories, 15 route states, desktop/mobile overlays, production search, manifest, RSS, links, build checks | pnpm check; pnpm lint; pnpm format; pnpm build; production preview http://127.0.0.1:4322; internal link crawl | Passed | 0 Astro diagnostics, 0 lint/format failures, build passed, 0 broken local refs, 0 console warning/error route regressions, all user-visible defects retested fixed.

## Legend
Legend
How to read and maintain the canonical QA workbook.
Field | Allowed Values / Meaning | When to use | Owner
Test Status | Not Tested; Build Verified; Needs Browser Verification; Defect Open; Fixed - Retest Pending; Verified; Deferred | Track where each user story is in the QA loop. | Codex
Fix Status | No Fix Needed; Open; Pending Fix; Fixed; Retest Pending; Deferred | Track whether source changes are needed or done. | Codex
Severity | Critical; High; Medium; Low; Cosmetic; N/A | Risk/impact if behavior is wrong. | Codex
Defect Status | Open; Fixed; Retest Pending; Verified; Deferred | Lifecycle for rows in Defect Log. | Codex
Evidence / URL | Browser URL, screenshot path, command, or note | Add immediately when testing or fixing. | Codex
Canonical rule | Only FEATURE_STATUS.xlsx is the source of truth | Do not fork parallel trackers. | All
QA rule | Test every listed user story before final sign-off | Desktop + mobile + light/dark where relevant. | Codex
Fix rule | One source-code fix per commit | Keep defects traceable. | Codex
Regression rule | Retest every user story post-fix | Final status cannot be complete before retest. | Codex
Design rule | Black/white editorial, experimental art, low clutter | Preserve homepage visual direction. | Codex
Audience | Collaborators and public visitors | Prioritize discoverability of work and reading. | Codex
Known build concern | GitHub token optional for releases/prs loaders | No-token builds show fallback copy. | Codex
Next update | Append deployment evidence if shipped | After production deploy/canary. | Codex